## Summary
MVP Project Plan — Library Resource & PC Access System
Project at a Glance
Modules | Features | Total Effort (Hrs) | Start Date | End Date
3 | 21 | 1176 | May 4th | June 30th
Module Breakdown
Module | Effort (Hrs) | Start | End
Module 1: User Kiosk | 152 | May 4th | May 29th
Module 2: Admin / Nerve Center | 780 | May 4th | June 12th
Module 3: PC Access | 244 | May 18th | June 18th
UAT, Fixes & Deployment Readiness |  | June 12th | June 30th
TOTAL MVP | 1176 | May 4th | June 30th

## MVP
Phase | Module | Feature / Screen | Scope | Total Efforts (Hrs) | Planned Start Date | Planned End Date
PHASE 1 (May 4 - May 22, 2026) |  |  |  | 152 | 2026-05-04 | 2026-05-29
1 | User Kiosk | Welcome screen | • Account Categorization: Implement a screen to choose between 'I have an account' or 'I do not have an account'. We implemented as Patron and guest • Customizable UI: Allow administrators to edit button text or skip the categorization screen entirely. • Inactivity Logic: System must reset to the 'Home' screen after a configured number of idle seconds. • Visible Timer: Provide an optional, on-screen countdown timer before the auto-reset occurs. • Categorization Bypass: Admin must have the option to skip the Patron/Guest selection screen entirely. • UI Flexibility: All button text for "Patron" and "Guest" must be fully customizable by the admin. | 20 | 2026-05-04 | 2026-05-05
|  | Login Screen for Patrons | • User Detection: System automatically identifies user type via ID patterns and applies the correct login rules. • Barcode Login: Support scanning of physical barcodes to automatically populate the ID field. • Instant Login: Single-click access for users without accounts (Guest Mode). • Privacy Purge: Anonymize and delete temporary guest accounts immediately after the session ends. | 24 | 2026-05-11 | 2026-05-13
|  | Resources Selection (PC, Printer, Conference) | • Type Filtering: Users select specific resource types (e.g., PC, Conference Room, or 3D Printer). • Contextual Rules: System applies specific time limits and eligibility rules based on the chosen resource. • Schedule Picker: Provide a date and time-slot selection interface for future bookings. | 32 | 2026-05-18 | 2026-05-21
|  | Reservation Management | • Use Now: Enable immediate session starts for resources that are currently available. • Book Later: Allow users to schedule future sessions based on system-wide availability. • Lead Time Rule: Restrict bookings based on how early or late the user is attempting to schedule. | 24 | 2026-05-18 | 2026-05-20
|  | Get Confirmation Details | • Reservation Display: Show a full summary of the reservation details on-screen after completion. • Email Dispatch: Allow patrons to send a confirmation email to themselves from the kiosk. • Live Tracking Link: The confirmation email must include a dynamic link that allows patrons to track their real-time waitlist position. • HTML Placeholders: Use customizable templates with placeholders: {patron_name}, {barcode}, and {barcode_last_four}. | 16 | 2026-05-21 | 2026-05-22
|  | Waitlist Management | • Automated Queue: Allow users to join a waitlist if all selected resource types are currently occupied. • FIFO Logic: Resources are assigned strictly in the order users joined the queue (First-In, First-Out). • Wait Time Range: Display estimated wait times as a range (e.g., '10–15 minutes') rather than a fixed value. | 16 | 2026-05-25 | 2026-05-26
|  | Existing Reservation Listing | • Active Bookings: Provide a dashboard for patrons to see all their upcoming and active sessions. • Detailed Info: Display specific resource and time information for every listed reservation. • Cancellation: Allow patrons to view and cancel their own bookings based on allowed rules. | 20 | 2026-05-27 | 2026-05-29
PHASE 2 (May 4 - May 31, 2026) |  |  |  | 780 | 2026-05-04 | 2026-06-12
2 | Admin/Nerve | Users Management | • User Account Management: Support creation, update, view, merge, delete, archive, anonymize, ban/reinstate users, including guest/visitor accounts with expiry, restrictions, and full profile, identity, and classification fields • User Search & Discovery: Provide quick search across logon ID, alias, name, email, phone, address, birthdate, and IDs, along with advanced multi-field search using AND/OR criteria and filters. • User Profile & Identification: Maintain core identity, personal information, multiple identifiers (barcode, QR, prox, gov ID, external IDs), authentication history, and configurable/custom fields. • User Groups, Types & Tiers: Manage user groups (session limits), user types (standard, guest, visitor, instant with lifecycle rules), and user tier. • User Actions & Reservations: Enable actions such as creating passes, reservations (scheduled, standby, group), viewing activity/history, and handling session tracking and user-related operations. • Bulk Operations & Data Handling: Support bulk actions including archive, anonymize, mass update, import users, export usage data, and lifecycle automation (expire, anonymize, purge). • Activity, Sessions & History: Track complete user history, authentication logs, session activity (current, upcoming, past), and maintain audit-level visibility of user interactions. | 100 | 2026-05-04 | 2026-05-20
|  | Resources Management | • Resource Configuration: Manage all reservable resources including authenticated (computers, workstations, laptops) and unauthenticated items (rooms, desks, devices, maker-space, A/V equipment) with type, location, area, and operational settings. • Resource Lifecycle Management: Support full lifecycle actions including create, update, view/history, disable/re-enable, replicate, link, rename, merge, delist, anonymize, destroy, return, and activate/deactivate with audit tracking. • Resource Types & Categorization: Define and manage resource types (authenticated/unauthenticated), configure reservation rules, scope (global, location, area, subgroup), and enable advanced search and filtering. • Licensing & Deployment: Assign, update (relicense), remove licenses, and manage previously licensed resources with proper device behavior handling. • Resource Operations & Bulk Actions: Enable bulk actions such as activate, disable, merge, license assignment, and support grouping (collections) for reporting and dashboard filtering. • Resource Visibility & Monitoring: Display real-time resource status (available, maintenance, offline), support search/filter by type, location, and area, and maintain detailed resource history, notes, asset/service tags, and metadata. • Access & Authentication Handling: Support both login-required and non-login resource categories with appropriate access and session behavior | 120 | 2026-05-04 | 2026-05-22
|  | Reservations Management | • Reservation Types & Modes: Support multiple reservation types including Block, Scheduled, Walk-up, Queued, Fill-in (Standby), Group, Maintenance, with flags for Assisted, Priority, and Waitlist to handle diverse booking scenarios and queue-based allocation. • Reservation Management: Enable creation, update, modification (add/release resources), cancellation, extension, sorting, and recovery of reservations including missed reservation handling. • Queue & Allocation Logic: Implement queue-based assignment, priority handling, standby (fill-in) allocation, and shared/free time usage when personal allocation is unavailable . • Reservation Status & Indicators: Display real-time statuses such as active, scheduled, queued, maintenance, assisted, overdue, and needs-attention with dashboard visibility and alert mechanisms. • Search, Filters & Views: Provide quick and advanced search, filtering by branch, type, date, and status, along with upcoming and recent activity views including alerts and patron details. • Time Rules & Controls: Support reservation extensions, grace periods, overdue detection, and enforce rules for session duration, thresholds, and automatic actions. • Activity & Monitoring: Track reservation lifecycle, display recent activity logs, highlight overdue or missed reservations, and enable recreation of reservations from past records. | 120 | 2026-05-04 | 2026-05-22
|  | Login Screen for Nerve Center Users / IT admins | • Credential Masking: Implement a standard username and password form where the password field masks all input for confidentiality. • RBAC Enforcement: Dynamically grant access to system features and modules based on the staff member's assigned role (e.g., Super Admin vs. Restricted Staff). • Account Lockout Logic: Automatically lock the account after three consecutive unsuccessful attempts and display instructions to contact the system administrator. • Access Control: Enforce strict data boundaries immediately upon login so staff can only view/modify data within their authorized scope. • Security Auditing: Implement mandatory logging for all login attempts (successful and failed), capturing the timestamp and user ID for audit trails. • Validation Messaging: Display clear, non-specific error messages for unauthorized users while validating credentials against the centralized staff database. | 80 | 2026-05-11 | 2026-05-22
|  | Dashboard | • Metric Card Widgets: Display real-time KPIs for Active Sessions, Available Now, System-wide Utilization Rate, and Offline/Maintenance counts. • Branch Occupancy Heatmap: Implement a real-time grid representing computer stations with the branch name and occupancy count (e.g., "28 / 60 occupied") clearly visible. • Heatmap Color Coding: Use standardized Red (Occupied), Green (Available), and Gray (Offline) colors with a clear legend. • Granular PC Support: Distinguish between Adult/Child PC types, Express PCs, and specific physical zones or floors. • Peak Usage Hours: Provide a panel showing predefined time slots with color-coded utilization percentages (Red/Orange/Blue). • Today's Statistics: Show cumulative Total Sessions, Avg. Session Time, and Queue Wait Time. • Recent Activity Feed: Scrollable log with timestamps, computer IDs, and visual icons/colors for session starts, reservations, and system alerts. • Configurable Auto-Refresh: Enable regular data updates at administrator-defined intervals without requiring page reloads. • Role-Based Filtering: Staff can filter by branch or computer group, strictly limited to their authorized scope based on permissions. | 60 | 2026-05-22 | 2026-06-02
|  | Locations | Locations: Manage branch/site records that represent physical library locations, including name, code, address, phone, website/public info, contact details, time zone, nearby sites, and status flags Location details: Create, view, edit, decommission, recommission, or disable a location; maintain basic location metadata, server assignment, and public-facing information used by staff and patrons. Branch Hours & Schedule: Define daily operating hours, opening/closing time rules, holiday closures, modified hours, shutdown schedules, and special exceptions; these settings drive reservation availability, access control, and automatic shutdown/reopen behavior. | 100 | 2026-05-22 | 2026-06-09
|  | Constructs | Portals: • Endpoint Management: Create access portals specifically for Kiosks or PC Access stations. • MVP Portal Sync: Link portals to specific locations; updates to the URI or location must reflect across all connected workstations instantly. • Secure Routing: Route all portal requests through encrypted workflows, ensuring the "Secure Connection" UI indicator remains valid. Workflows: • Auth Handling: Create workflows for authentication, field mappings, and integration routing. • MVP Reverse Lookup: Configure rules to match incoming patron IDs against external databases (like SIP2) instantly. • Step Validation: Workflow updates must include a "Test Mode" to verify integration routing before going live. Segments: • Network Routing: Define access segments that control how servers and workstations connect. • MVP Logic: Implement "Route Behavior" rules that prioritize traffic for active sessions over background system updates. • Safety Check: Enforce a "No Dependencies" rule preventing segment deletion if active workstations are still assigned. | 120 | 2026-05-22 | 2026-06-11
|  | System | • System Configuration: Manage organization details, hierarchy (locations, areas), system preferences, environments, database settings, networking configurations, and documentation/help. • Security Management: Configure 2FA (including email priority), authentication methods (password, PIN, external), password policies, advanced security settings, and enforce access control across organization, location, and user tiers. • Integrations & Email: Manage external system integrations, authentication services, email configuration (SMTP, OAuth, EWS, Entra), messaging, email templates, and authorized contact data exports. • Automation & Operations: Execute system scripts, scheduled tasks, bulk user import, data anonymization (options and scheduling), keyword management, and workstation behavior configurations. • Monitoring & Logging: Monitor system logs, configure audit trails, log file prefixes by location, and track administrative and system activities for compliance. • Access & UI Settings: Support settings hierarchy with inheritance, role-based and zone-based access control, and manage language preferences, theming, and UI customization | 80 | 2026-06-01 | 2026-06-12
PHASE 3 (May 4 - June 15, 2026) |  |  |  | 244 | 2026-05-18 | 2026-06-18
3 | PC Access | Welcome Screen | • Visual Status Indicators: Display high-visibility color-coded frames (Blue for Available, Orange for Unavailable) visible from 30–50 feet. • Standardized UI: Show Customer Label, description, available duration (e.g., "60 min"), and internal hostname with timezone. • Staff Access: Provide dedicated login shortcuts for Librarians/Admins and allow remote enable/disable with real-time screen updates. • Accessibility: Support language selection (Spanish) and 4K-optimized zoom/sizing controls for vision needs. | 36 | 2026-05-18 | 2026-05-22
|  | Policy | • Rich Text Content: Support fully customizable library policies with rich text formatting (cut/paste from admin portal). • Acknowledgment Logic: Optional "Force Scroll" requirement where the "I Accept" button remains inactive until the user reaches the end of the text. • Configurable Actions: Button labels ("Cancel" / "I Accept") must be customizable; include an optional footer for non-clickable policy links. | 12 | 2026-05-21 | 2026-05-22
|  | Login | Credential Entry: Support library barcode/username and masked password fields with customizable placeholder hint text. • Security Trust: Prominently display a "Secure Connection" indicator to assure patrons of data encryption during transmission. • Navigation: Provide "Back" and "Exit" buttons to return to the welcome screen or cancel the login workflow entirely. | 16 | 2026-05-25 | 2026-05-26
|  | Time Tracker | • Advanced Countdown: Display MM:SS timer with a "Session Options" button and a shrinking (not counting up) high-visibility progress bar. • Color Progression: Green (>50%), Blue (Mid-threshold), Yellow (Low: 10m), and Red (Critical: 5m) with flashing alerts at threshold transitions. • Engagement Logging: Flashing stops if clicked; the system logs this as audit proof that the patron was warned of remaining time. • UI Priority: Timer must use the highest Z-index to stay visible above full-screen videos and all other applications. | 36 | 2026-05-27 | 2026-06-02
|  | Extension Wizard | • Utilization-Based Tiers: Dynamically offer Simple, Standard, or Long extensions based on library load (e.g., disable all if >90% computers are in use). • User Feedback: Unavailable options must be grayed out with specific reasons (e.g., "Not available due to high demand") and current utilization stats. • Validation & Limits: Enforce per-session (e.g., max 2) and per-day (e.g., max 4 hours) extension limits with automated server-side validation. | 52 | 2026-06-02 | 2026-06-09
|  | Work Saving & Logout | • Grace Period Prompt: Trigger a 2-3 minute countdown prompt at 00:00 or upon remote termination to allow patrons to save work. • Logout Options: Offer "I’ve Saved My Work" for immediate exit or "I Need More Time" to bridge back to the Extension Wizard. • Forced Termination: Upon grace period expiry, force-close all apps, scrub temporary user data, and return machine to "Available" status. | 52 | 2026-06-10 | 2026-06-15
|  | System Stability | • Crash Recovery: Maintain session records on the server; if a machine reboots, it must remain reserved for the patron with the remaining time tracked. | 40 | 2026-06-16 | 2026-06-18
|  | TOTAL |  | 1176 | 2026-05-04 | 2026-06-18
Formulas:
Planned Start Date = MIN([Planned Start Date, row below]:F9)
Planned End Date = MAX([Planned End Date, row below]:G9)

## Gantt
Gantt Chart — MVP Delivery Timeline
[6 empty] | 2026-05-01 | [27 empty] | 2026-06-01
| Task | Start | End | Days | Hrs | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
| Module 1: User Kiosk | 2026-05-04 | 2026-05-29 | 26 | 152
| Welcome screen | 2026-05-04 | 2026-05-05 | 3 | 20
| Login Screen for Patrons | 2026-05-11 | 2026-05-13 | 3 | 24
| Resources Selection (PC, Printer, Conference) | 2026-05-18 | 2026-05-21 | 4 | 32
| Reservation Management | 2026-05-18 | 2026-05-20 | 3 | 24
| Get Confirmation Details | 2026-05-21 | 2026-05-22 | 2 | 16
| Waitlist Management | 2026-05-25 | 2026-05-26 | 2 | 16
| Existing Reservation Listing | 2026-05-27 | 2026-05-29 | 3 | 20
| Module 2: Admin / Nerve Center | 2026-05-04 | 2026-06-12 | 38 | 780
| Users Management | 2026-05-04 | 2026-05-20 | 13 | 100
| Resources Management | 2026-05-04 | 2026-05-22 | 15 | 120
| Reservations Management | 2026-05-04 | 2026-05-22 | 15 | 120
| Login Screen for Nerve Center Users / IT admins | 2026-05-11 | 2026-05-22 | 10 | 80
| Dashboard | 2026-05-22 | 2026-06-02 | 8 | 60
| Locations | 2026-05-22 | 2026-06-09 | 13 | 100
| Constructs | 2026-05-22 | 2026-06-11 | 15 | 120
| System | 2026-06-01 | 2026-06-12 | 10 | 80
| Module 3: PC Access | 2026-05-18 | 2026-06-18 | 23 | 244
| Welcome Screen | 2026-05-18 | 2026-05-22 | 5 | 36
| Policy | 2026-05-21 | 2026-05-22 | 2 | 12
| Login | 2026-05-25 | 2026-05-26 | 2 | 16
| Time Tracker | 2026-05-27 | 2026-06-02 | 5 | 36
| Extension Wizard | 2026-06-02 | 2026-06-09 | 7 | 52
| Work Saving & Logout | 2026-06-10 | 2026-06-15 | 5 | 52
| System Stability | 2026-06-16 | 2026-06-18 | 2 | 40
| UAT, Fixes & Deployment Readiness | 2026-06-12 | 2026-06-30 | 20 | —
| Legend: | Module 1 — User Kiosk | Module 2 — Admin / Nerve Center | Module 3 — PC Access | UAT / Buffer
• Schedule assumes 8 productive hours per day per developer (1 person per feature).
• Module 1 runs as a single sequential track. Modules 2 and 3 use parallel tracks where serial work would exceed the calendar window.
• Module 2 uses 4 tracks (3 backend + 1 frontend for Dashboard). Module 3 uses 2 tracks (frontend/UI + backend/desktop client).
• Last development day: Wednesday, June 10, 2026. UAT, fixes, and deployment readiness run through Tuesday, June 30.

## MVP2
Phase | Module | Feature/Screen | Functionality | Scope | Yet to Start | Development | QA | Review | Completed | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date
Phase 1
1 | User-kiosk | Resource Booking Screen | Compound Booking | User can book multiple resources together if all are available. | Agreed
|  | Waitlist Screen | Spillover Assignment | System assigns user to another available resource if preferred one is not available. | Needed but not by July 1st
|  | Account Creation Screen | Self-Service Account Creation | Patron who does not have an account can create one directly at the kiosk via a dedicated button or full screen (On-Demand User Generation: Disabled / Kiosk button / Screen). | Needed - Should be MVP
Phase 2
2 | Admin and Nerve Center | Dashboard | Near Branches Display | Show nearby branch status with toggle control. | Agreed
|  |  | Heatmap Zoom | Allow zoom in/out with real-time preview and variable density view. | Agreed
|  |  | Heatmap Grouping | Group tiles by area, pool, status, or duration state. | Agreed
|  |  | Heatmap Sorting | Sort by resource name, status, type, or remaining time with multiple criteria. | Agreed
|  |  | Heatmap Filtering | Filter by area, reservation type, status, and resource type using checkboxes. | Agreed
|  |  | Legend Display | Show or hide legend placement on the heatmap header or between widgets and heatmap. | Agreed
|  |  | Widget Visibility | Show or hide side widgets and top widgets while ensuring at least one widget remains visible. | Agreed
|  |  | Details Toggle | Show or hide reservation details such as letter code, time symbol, and owner information. | Agreed
|  |  | Hover Popup | Show clipboard copy, user navigation, resource navigation, and notes/details in hover popup. | Agreed
|  |  | Session Timer Symbols | Display circle, pentagon, square, and triangle symbols based on remaining time thresholds. | Out of Scope
|  | Resources | Compound Resource Create | Create static or dynamic compound resource definitions. | Agreed
|  |  | Compound Resource Rules | Define membership rules and availability evaluation. | Agreed
|  |  | Compound Resource Manual Members | Allow direct resource selection into compound resource membership. | Agreed
|  |  | Compound Resource Dynamic Members | Allow type-based dynamic membership across scope. | Agreed
|  | Constructs | Zone Create | Create administrative zones defining where tier permissions may be exercised. | Needed but not by July 1st
|  |  | Zone Update | Edit zone scope and included locations, pools, or areas. | Needed but not by July 1st
|  |  | Zone Delete | Remove unused zones with permission dependency checks. | Needed but not by July 1st
|  |  | Zone Mapping | Map zones to one or more locations, pools, or areas. | Needed but not by July 1st
|  | Reservations | Waitlist Spillover | Move queue to other areas/resources based on pool and spillover rules. | Needed but not by July 1st
|  | Reports | Report Create | Create a new report definition with filters and output format. | Needed - Should be MVP
|  |  | Report Update | Edit report definition, filters, and display settings. | Needed - Should be MVP
|  |  | Report Delete | Remove report definitions safely. | Needed - Should be MVP
|  |  | Report Run | Execute a report immediately using current filters. | Needed - Should be MVP
|  |  | Report Schedule Create | Create scheduled report execution jobs. | Needed but not by July 1st
|  |  | Report Schedule Update | Modify report scheduling rules and delivery settings. | Needed but not by July 1st
|  |  | Report Schedule Remove | Remove report schedules. | Needed but not by July 1st
|  |  | Report Filters | Filter reports by location, area, pool, resource type, collection, group, or resource. | Needed - Should be MVP
|  |  | Report Sort | Sort report listings by name, type, last run date, or schedule. | Needed - Should be MVP
|  |  | Report Export | Export report output for staff processing. | Needed - Should be MVP
|  |  | Usage Export | Export usage and account data for external use. | Needed - Should be MVP
|  |  | Current Activity Report | Report on current activity, queue, and live reservation data. | Needed - Should be MVP
|  |  | Historical Activity Report | Report on last 30 days or full history. | Needed - Should be MVP
|  |  | Reservation Transaction Report | Track session type, duration, extension count, and timing fields. | Needed - Should be MVP
|  |  | Reporting Groups | Use reporting groups and resource collections for staff oversight. | Needed - Should be MVP
|  | Users | User Tier Create | Create a permission level or role. | Needed but not by July 1st | Can start with multiple hardcoded levels and add the ability to customize after the initial beta.
|  |  | User Tier Update | Modify tier permissions and accessibility. | Needed but not by July 1st
|  |  | User Tier Delete | Remove a tier only when unused. | Needed but not by July 1st
|  |  | User Type Create | Create standard or special account types. | Needed - Should be MVP
|  |  | User Type Update | Configure lifecycle rules for user types. | Needed - Should be MVP
|  |  | User Class/Criteria | Configure class matching and calculated criteria. | Needed - Should be MVP
|  |  | Bulk User Actions | Mass update, import, export, and other bulk operations. | Needed but not by July 1st
|  |  | Display Processing Server | Display which server is currently processing requests for the viewed portal/session. | Needed but not by July 1st
|  | Locations | Pools Admin | Provide full CRUD and configuration of pools used for queue spillover, grouped oversight, and kiosk assignment. | Needed but not by July 1st
|  |  | Location Override Report Schema | Allow location-level override reporting or schema selection where data partitioning/report logic requires it. | Needed but not by July 1st
|  | System | Experiences | Manage experience-specific settings for kiosk, staff, and reservation interfaces. | Needed but not by July 1st
|  |  | Servers | Manage server definitions, active state, routing preference, and maintenance handling. | Needed but not by July 1st

## Out of Scope
Phase | Module | Feature/Screen | Out of Scope | In Scope | Out of Scope
1 | Security | Unique ID Handling | Implement secure handling of user identifiers using encryption or hashing, and maintain a history of ID changes. This ensures data security while allowing traceability of user identity updates over time | Implement secure handling of user identifiers using encryption or hashing, | maintain a history of ID changes. This ensures data security while allowing traceability of user identity updates over time
2 | Infrastructure | API Configuration | Enable secure API access using token-based authentication with configurable expiry and role-based permissions. This ensures controlled and secure communication between system components.
3 | Admin | System Actions | Provide centralized administrative controls to perform system-wide actions such as shutdown, logoff, reboot, and wake operations. The system should notify active users before execution and ensure safe handling of ongoing sessions.